Stage 3B — Situation Evaluation (v2)

Prepared 13 September 2026 for Prof. C. F. Cheung · Sidney K. T. Tam. Supersedes the same-day v1: the deployed build, distribution chronology and first return have since been verified against records.

1. What Stage 3B is and why

Stage 3A (March–April 2026) showed engagement holds when the FRA verdict is removed from play — but removal cannot serve users who need the measurement, and it did not test the Chapter 7 adaptive-learning framework. Stage 3B, designed in August 2026 once the 3A results made that gap precise, evaluates the framework's middle ground: measurement kept visible while the system adapts to the player (calibrated challenge, trajectory framing, coaching). It is a separately labelled exploratory randomised evaluation; the reported 3A record is untouched. Hypothesis H-3B and a single confirmatory contrast (adaptive vs static on stated regular-play intention, pooled across a secondary failure-mode factor) were pre-specified in the repository on 9 August 2026, before any recruitment.

2. Established facts (verified against records)

Deployed artifact. Distributors received device copies Alpine3B_DEV1…DEV5.html of the build generation repository-dated 9 Aug 2026 07:09 — one self-contained game file with in-build consent, enrolment, silent 2×2 randomisation (adaptive/static support × zero-fail/game-over-possible), 30-second runs, end-screen questionnaire, and a per-device participant archive. Verified by matching the first return's field structure to that generation's export code; the two 13-August build amendments post-date distribution and were not deployed (to be recorded as such).

Chronology. Analysis plan committed 9 Aug 07:20 → first recruitment message (WeChat, archived) 9 Aug afternoon → game files sent to distributors 10–12 Aug → first return 15 Aug. Specification preceded recruitment; the WeChat records are archived as received.

Distribution model. About twenty volunteer helpers forwarding to their own networks; roughly one hundred recipients estimated; per-helper counts being collected. Facilitated play on shared devices is supported by the build's device archive; ethics coverage: HSEARS20260805008, approval period to 30 October 2026.

3. First verified return — chain of custody (participant B9V8YA)

| Link | Record |
| --- | --- |
| File sent | Alpine3B_DEV2.html to distributor Huang, WeChat, 10 Aug 23:35 (screenshot archived) |
| Consent + play | 15 Aug, in-build timestamps; enrolment 45–64/F; one 30-s session; arm B (static), zero-fail cell; questionnaire complete |
| Return | Verbatim return text e-mailed to sidney.tam@connect.polyu.hk, 15 Aug 17:06 (original e-mail archived) |
| Verification | Field structure matches the deployed build generation exactly (arm, failure-mode, scoring identity); archived as received |

4. Open items

Returns received to date (count being compiled); harvest exports from each device via the facilitator panel (instruction issued to helpers); per-helper participant counts; the collection close date. No analysis has been performed and none will be before your sign-off; the pre-specified plan is the gate. Realistic return scenarios: N ≥ 40 supports the pre-specified contrast; 20–39 is reported as underpowered with interval estimates; below 20 is exploratory/descriptive. The framing rule will be fixed on the observed N, before analysis.

5. Decisions requested

(1) Your signature on the mini-protocol (§9, attached). (2) The collection close date — suggested mid-October, leaving margin for returns and archiving before the ethics period ends 30 October. (3) Your steer on how Stage 3B appears in Saturday's review — the slides show status only, no results.