Thesis Completion Timeline

Milestone plan supporting the extension application · August 2026 · Months are relative to the grant of extension

| Period | Milestone | Work content |
| --- | --- | --- |
| Month 1 | Stage-3 data archive | Compile the participant-level Stage-3 logbook from distributor returns with transmittal evidence; reconcile against the published register; complete the fourth expert-consultation record (consent + summary). |
| Month 2 | Appendices | Assemble Appendices A-D (verbatim instruments, coding records, reliability statistics) and Appendix G (data, consent and AI archive); apply queued wording corrections from the revision tracker. |
| Month 3 | Verification and production | Full verification sweep (statistics against source data; citation-reference audit; internal consistency); regenerate tables of contents, lists of figures and tables; complete proofread. |
| Month 4 | Supervisor review | Chief Supervisor's review of the complete thesis; incorporate revisions arising. |
| Month 5 | Submission | Final production pass and submission for examination; margin retained for administrative processing. |

Parallel activity throughout: submission of the Stage-2 paper to the Journal of Information & Knowledge Management (ethics reference in hand) and correspondence arising.