Stage 3B Evidence Verification — Plan and Checklist

Prepared 12 September 2026. Purpose: establish, from records rather than recollection, what the August 2026 deployment was, so its data can be classified against the Stage-3B protocol and analysed. Four evidence categories: deployment records, protocol chronology, measurement documentation, approval memo.

A. Already established — repository-dated (no action needed)

| Item | Evidence | Location |
| --- | --- | --- |
| Protocol draft (incl. two-arm Option A / single-arm Option B) | Git commit 473046c, 8 Aug 2026 12:54 | docs/thesis/stage3b/Stage3B_Mini_Protocol_DRAFT.docx |
| v3.0 build: in-build consent, silent arms, questionnaire, one-file export | Commit 6ef4f3f, 9 Aug 2026 06:09 | docs/thesis/game/Alpine_Coordination_Game_v3.0_Stage3B_bilingual.html |
| Pre-specified inferential hierarchy (single confirmatory contrast) | Commit 13a6e91, 9 Aug 2026 07:20 | Protocol §7 |
| 2×2 failure-mode factor; shared-device support | Commits 59b7881 / abf1603, 9 Aug 2026 | Protocol §3; build |
| Score system finalised (gains-only) + input-modality logging | Commits of 13 Aug 2026 (923a25e, a1afc42) | Protocol Amendments A/B |
| Ethics approval memo: HSEARS20260805008, approved 6 Aug 2026, period 16 Jun 2024 – 30 Oct 2026, PI Prof. Cheung | Archived as-received 11 Sep 2026 | docs/thesis/ethics/ |

The one chronology fact the repository cannot supply is the deployment start date — item B1 below. Until it is documented, the claim “specification preceded recruitment” stays unasserted.

B. To collect from the field — in priority order

B1. The distribution record. Find the original message(s) that sent the game out in August — e-mail, WhatsApp or WeChat — and forward them as files or screenshots, timestamps visible. Establishes: the artifact actually distributed, the start date, and the recruitment chronology.

B2. The deployed artifact. Ask one distributor (or take from the sent message) the exact game file or link participants received, unmodified. I will compare it byte-for-byte against the repository builds — this settles conclusively which procedures participants experienced.

B3. The returned records. Every return received so far, exactly as received (JSON files, or pasted results text, unedited). Even one return is diagnostic: a 3B return contains a consent event, enrolment fields, an arm assignment and questionnaire answers; a 3A-style return does not. All returns will be archived as-received and logged in the invitation-and-returns template (docs/thesis/stage3b/Stage3B_Invitation_and_Returns_Log_TEMPLATE.xlsx; use the device-rotation log if shared devices were used).

B4. Deployment facts. Who distributed, through which channels, what recipients were told (the consent basis), and roughly how many have participated so far. A few sentences by message is enough; I will structure them.

C. Measurement documentation

Stage 3B: the measurement is defined inside the artifact itself (score formula per Amendment A; D1/D2 and framework items with scales) — verifying B2 verifies the measurement. Stage 2 comparison (the +4.03 index change): supported by the archived FRA logbook and entry workbook; to complete it, obtain the InBody index specification (vendor manual or spec sheet from the centre) documenting the composite index and its scale direction.

D. What happens on receipt

(1) Hash/feature comparison of the deployed artifact against the repository builds; (2) shape-check of returns; (3) classification fixed on that evidence and recorded; (4) interim wording in the deck and thesis replaced with the verified deployment details; (5) everything archived as-received with a short verification memo suitable for the panel and the supervisor.